## Cover
ADY201m Lab 4

## Change
Change history
# | Creator | Version | Date | Change contents
1 | Huynh Quoc Trung | 1 | 20/05/2024 | Create new estimation
3
4
5
6
7

## Estimation
Detail Coding Estimation
Fucntion Information |  |  |  |  | Option-1 Est (MD) | Plan |  | Actual |  | Status | Note
No | Category | PIC | Role | To Do List |  | Start date | End date | Start date | End date
1 | Collect Data | FPTU
|  | YCN |  | Meeting and divide task for each person |  | 2024-06-04 | 2024-06-04 | 2024-04-06 | 2024-04-06 | 100%
ViVMK
TrungHQ
2 | Data Understanding | FPTU
|  | YCN |  | Data ETL |  | 2024-06-05 | 2024-06-06 | 2024-06-05 | 2024-06-06 | 100%
4 | Clean data | FPTU
|  | ViVMK |  | NLP handle and build model |  | 2024-06-06 | 2024-06-08 | 2024-06-06 | 2024-06-08 | 100%
5 | Write query | FPTU
|  | TrungHQ |  | Using flask framework to build API and make web application to deploy model |  | 2024-06-08 | 2024-06-09 | 2024-06-08 | 2024-06-09 | 100%
6 | Presentation | FPTU
|  | YCN |  | Make slide and demo |  | 2024-06-09 | 2024-06-09 | 2024-06-09 | 2024-06-09 | 100%
ViVMK
TrungHQ
DA
Total Man Days
Formulas:
End date = [Plan]
End date = [Plan]+1
Actual = [Plan]